## Lean
Staffing Variant: Lean
Bet: Optimises strictly for commercial budget (15% Onshore / 15% Nearshore / 70% Offshore); trades schedule margin by pushing site cutovers to Month 12.
Role | Grade / Location | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | Total FTE-Mo
Delivery Lead | Lead (Onshore) | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Enterprise Architect | Senior (Onshore) | 0.5 | 0.5 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
Integration Tech Lead | Senior (Nearshore) | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Backend / API Dev (2x) | Middle (Offshore) | 0.3 | 0.8 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0.5 | 0.2
Frontend Portal Dev (2x) | Middle (Offshore) | 0 | 0.3 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 0.5 | 0.5 | 0.2
AI / Data Engineer | Senior (Offshore) | 0 | 0.2 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0.5 | 0.2 | 0.1
QA Automation Lead | Middle (Offshore) | 0.2 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
TOTAL MONTHLY FTEs

## Balanced
Staffing Variant: Balanced
Bet: Optimises for predictable milestone delivery on hard 12-month contract deadline using EPAM blended model (30% Onshore / 40% Nearshore / 30% Offshore). RECOMMENDED.
Role | Grade / Location | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | Total FTE-Mo
Delivery Manager | Lead (Onshore) | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1
Enterprise Architect | Lead (Onshore) | 1 | 1 | 0.5 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.25 | 0.25 | 0.25
Business Analyst / PROD | Senior (Onshore) | 0.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25
Integration Tech Lead | Senior (Nearshore) | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
Backend / API Devs (3x) | Middle (Nearshore) | 0.5 | 1.5 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 0.5
Frontend Portal Devs (2x) | Middle (Offshore) | 0 | 0.5 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0.5 | 0.2
AI / Data Engineer (2x) | Senior (Offshore) | 0 | 0.5 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 0.5 | 0.25
QA Lead & Automation (2x) | Senior/Mid (Nearshore) | 0.3 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0.5
TOTAL MONTHLY FTEs

## Fast
Staffing Variant: Fast
Bet: Optimises for schedule compression and early site enablement via high onshore co-location (50% Onshore / 30% Nearshore / 20% Offshore); trades higher burn.
Role | Grade / Location | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | Total FTE-Mo
Program Manager | Principal (Onshore) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.25
Enterprise Architect | Lead (Onshore) | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.25 | 0.1
Onshore Integration Leads (2x) | Lead (Onshore) | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0.5 | 0.5 | 0.25
Backend API Devs (4x) | Mid/Sr (Nearshore) | 1 | 3 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 0.5 | 0.25 | 0.1
Frontend Devs (3x) | Mid (Nearshore) | 0.5 | 2 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 0.5 | 0.2 | 0.1
AI Engineers (3x) | Senior (Onshore/NS) | 0.5 | 1.5 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0.5 | 0.2 | 0.1
QA Engineers (4x) | Mid (Offshore) | 1 | 2 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 0.5 | 0.25
Change & Training Lead | Senior (Onshore) | 0.25 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.25
TOTAL MONTHLY FTEs

## Summary & Recommendation
Staffing Variants Trade-Off & Recommendation
Metric / Dimension | Lean Variant | Balanced Variant (Recommended) | Fast Variant
Total FTE-Months
Delivery Model Split | 15% On / 15% NS / 70% Off | 30% On / 40% NS / 30% Off | 50% On / 30% NS / 20% Off
Target Go-Live Schedule | Month 12 (High Cutover Risk) | Month 11 + 4 Wk Buffer | Month 9.5 (2.5 Mo Early)
Commercial Cost Index | 1.00x (Baseline) | 1.55x | 2.35x
Primary Delivery Risk | Resource bottleneck in M12 | Balanced risk profile | Excessive client coordination load
Delivery Lead Recommendation
We strongly recommend the BALANCED VARIANT (99.0 FTE-Months). • Lean Variant (60.7 FTE-Mo) creates an unacceptably high risk profile. Its 70% offshore split without dedicated onshore BA in Months 1–2 will cause legacy schema discovery bottlenecks that endanger the hard 12-month deadline. • Fast Variant (139.3 FTE-Mo) compresses schedule to 9.5 months but increases cost by +52% over Balanced and places an unrealistic operational burden on site leads for parallel UAT. • Balanced Variant achieves optimal trade-off: dedicated onshore architecture during Discovery (Phases 1–2), nearshore tech leads for real-time client collaboration, and a 4-week schedule buffer prior to contract expiry.