## Estimate Summary
EU Machinery Corp — Commercial Delivery Estimate
Basis: Balanced Staffing Variant (99 FTE-Months) across 4 Phases
Line Item / Delivery Component | Basis / Unit | Quantity / Rate | Total Cost (€)
Phase 1: Discovery & Architecture Foundation | FTE-Months (Blended) | 11.3 | 113000
Phase 2: Integration Backbone & Portal Build | FTE-Months (Blended) | 57 | 570000
Phase 3: AI Assistant Engine & Regulatory Audit | FTE-Months (Blended) | 20.75 | 207500
Phase 4: Multi-Site Pilot & Production Cutover | FTE-Months (Blended) | 9.95 | 99500
SUBTOTAL BASE EFFORT | 99.0 FTE-Mo @ €10,000/mo avg
Ramp-up Productivity Lag Impact | 5% of Base Effort | 0.05
Sub-Vendor Coordination (CyberGuard EU) | 3% of Base Effort | 0.03
Client Dependency Wait & UAT Buffer | 4% of Base Effort | 0.04
SUBTOTAL BASE + DELIVERY IMPACTS
Outsourced AI Act Compliance Audit (CyberGuard EU) | Subcontractor Pass-Through | 1 | 45000
Azure AI Search & OpenAI Gateway Inference Reserve | Gateway Log Sourced (M800) | 1 | 25000
TOTAL DIRECT DELIVERY COST
Contingency Reserve (Risk Protection) | 15% on Direct Delivery Cost | 0.15
TOTAL COST WITH RISK CONTINGENCY
Target Commercial Margin (Profit) | 22% Margin on Project Value | 0.22
TOTAL FIXED-PRICE PROPOSAL VALUE | Fixed-Price Milestone Fee

## Risk Register
Delivery Risk Register & Contingency Sizing
Risk ID | Risk Description | Likelihood (1–5) | Impact (1–5) | Score (L×I) | Active Mitigation Strategy | Contingency Allocation (€)
RSK-01 | Undocumented Legacy ERP Middleware Schemas | 4 | 4 |  | Mandatory 4-week architectural discovery phase in M1; freeze legacy schemas prior to Phase 2 build. | 45000
RSK-02 | AI Sales-Ops Quote Hallucination / Pricing Errors | 3 | 5 |  | Implement Azure AI Search RAG guardrails, deterministic pricing lookup tables, and mandatory HITL approval for quotes >€5k. | 35000
RSK-03 | Multi-Site UAT Bottlenecks Across 9 EU Sites | 3 | 4 |  | Phased site rollout (Site 1 Pilot, followed by 2 site clusters); mandatory 5-day defect logging SLA. | 30000
RSK-04 | Third-Party EU AI Act Regulatory Audit Delay | 2 | 4 |  | Shift sub-vendor (CyberGuard EU) to continuous checkpoint audits starting Month 6 rather than end-of-project gate. | 25000
RSK-05 | Azure Landing Zone Admin Access Provisioning Delays | 2 | 3 |  | Prerequisite dependency in contract: Azure access required within 10 business days of kickoff. | 15000
TOTAL SIZED CONTINGENCY

## Assumption Register
Contractual & Delivery Assumptions (Bounded)
ID | Category | Bounded Assumption Statement | Falsifiable Condition / Threshold | Impact if Breached
ASM-01 | Client Resources | Client provides dedicated legacy ERP domain specialists during Discovery & UAT. | Minimum 15 hours/week availability in M1–M2 and M10–M12. | Schedule delay; Change Request for additional EPAM analysis hours.
ASM-02 | Data Readiness | Client provides validated, cleansed, machine-readable price books. | Client PO formal sign-off on cleansed dataset by end of Month 2. | Phase 3 AI indexing delayed; client bears cleansing remediation costs.
ASM-03 | Turnaround SLA | Client site leads review and log UAT defects within agreed SLA window. | Max 5 business days per site review cycle; unlogged items deemed accepted. | Site cutover timeline extended; project delay fee applied.
ASM-04 | Environment | Azure enterprise tenant with admin privileges is provisioned promptly. | Full tenant access granted within 10 business days of contract award. | Day-for-day project milestone shift.
ASM-05 | Scope Boundaries | Legacy ERP underlying database schemas remain frozen during development. | Zero unannounced schema modifications between Month 2 and Month 12. | API middleware build rework billed under T&M rate card.

## Commercial Model Matrix
Commercial Model Decision & Fit Analysis
Commercial Model | RFP Alignment | Delivery Risk Fit | Cash-Flow Fit | Recommendation Status
Pure Time & Materials (T&M) | Low (RFP requires fixed-price) | High (Client carries scope risk, EPAM carries no margin risk) | Poor (Unpredictable buyer billing) | REJECTED (Fails RFP Constraint)
Pure Capped Fixed-Price | High (Buyer preferred) | Low (EPAM carries all legacy discovery risk) | Good (Predictable milestone payments) | REJECTED (Unbounded Legacy Risk)
Hybrid Milestone Fixed-Price (Gated) | HIGH (Fully satisfies RFP) | HIGH (Fixed-price milestones bound by Assumption Register) | EXCELLENT (Tied to 4 phase exit gates) | RECOMMENDED COMMERCIAL MODEL