## 05-backlog
Rank,Story,Reach,Impact,Confidence,Effort,RICE Score,Rationale
1,Story 11 - Clear "unknown" vs false "in stock",40000,3,0.8,1,96000,"Trust-repair for Persona A at near-zero incremental effort once Story 2's threshold exists; directly prevents the fail-open that causes phantom-stock cancellations."
2,Story 10 - No personal data in prediction (EU/JP consent),60000,2,1.0,2,60000,"Compliance gate across all 22 countries at 100% confidence — a legal must-have that also unblocks EU/JP rollout entirely; not optional regardless of score."
3,Story 2 - Told when system is unsure (the refusal contract),40000,3,1.0,3,40000,"The explicit 'unknown' state is the core differentiator and fail-safe; highest confidence because AC-2's >=95% gate and fail-safe default are already fully specified."
4,Story 1 - Show collectability verdict,50000,3,0.8,4,30000,"Core capability reaching every click-&-collect shopper and directly targeting the 7%->2% metric; 80% confidence reflects unproven per-region verdict accuracy until the golden set runs."
5,Story 3 - Store-specific verdict (no regional average),45000,2,0.8,3,24000,"Prevents the documented 'regional-average leak' adversary finding; per-store granularity is what makes the verdict actionable rather than a blurred market average."
6,Story 8 - Multilingual verdict (EU/JP),35000,1,0.8,2,14000,
7,Story 9 - Refresh verdict on return (stale data),25000,1,0.8,2,10000,
8,Story 4 - Verdict survives to pickup,30000,3,0.5,5,9000,
9,Story 5 - Fast check on slow connection (latency),30000,1,0.8,3,8000,
10,Story 12 - Flag reserved-but-uncertain for associates,8000,2,0.5,3,2667,
11,Story 6 - Log verdicts + confidence for audit,5000,1,1.0,2,2500,
12,Story 7 - Suggest alternative nearby store,20000,1,0.5,4,2500,
--- AI CRITIQUE (Step 4) ---
Row critiqued,Prompt asked,AI finding,My decision
Highest-score (Story 11),"Effort=1 gives it #1 — what dependency am I ignoring?","Story 11 can't be 1 p-mo alone; it depends on Story 2's confidence threshold + Story 1's verdict rendering. Its low effort is only true AFTER the AI capability ships.","Kept the score but documented that Story 11 sequences AFTER Stories 1+2. Framework flagged value, not build order."
Lowest-confidence (Story 4),"Story 4 is 50% confidence but IS the success metric (<=2% cancellations) — should low rank override its importance?","No — Story 4 measures the outcome the whole feature exists for. Low RICE reflects dependence on stock-drift outside the assistant's control, not low value.","Override noted: monitored as the outcome commitment despite rank #8."